TIMETABLE AND CHECKLIST

$1,750,000

TOWN OF MCCORDSVILLE, INDIANA

GENERAL OBLIGATION BONDS, SERIES 2022

Date	Action

Late August/early

September	Bond Ordinance and Appropriation Ordinance prepared; financial parameters prepared; schedule of proposed projects prepared; municipal advisor prepares initial draft of Term Sheet - Done

September 13	Meeting of Town Council to introduce Bond Ordinance and Appropriation Ordinance; set date for public hearing on additional appropriation of Bond proceeds

September 20	Notice of public hearing on additional appropriation of Bond proceeds published in the Daily Reporter

By October 10	Term Sheet finalized and distributed to potential bidders

October 11	Meeting of Town Council to hold public hearing on additional appropriation of Bond proceeds; adopt Bond Ordinance and Appropriation Ordinance

October 18	Notice of determination to issue Bonds published (first time) in the Daily Reporter; notice posted in 3 public places in the Town

October 19	Town selects financial institution to purchase the Bonds based upon responses to Term Sheet; closing date scheduled and closing documents prepared

October 25	Notice of determination to issue Bonds published (second time) in the Daily Reporter; notice posted in 3 public places in the Town

Week of October 25	Bond documents circulated for signature

Week of November 7	Pre-Closing

Week of November 7	Closing

Assumptions:

- All bodies comply with Indiana Open Door Law

- No project is a controlled project

- Bond issue is within Town’s constitutional debt limit (i.e., par amount of bonds, together with other general obligation indebtedness of the Town, is not greater than 1/3 of the Towns’ net assessed value)

- Bonds sold by negotiated sale through Term Sheet bid process; purchaser will be required to sign a sophisticated investor letter

- Rating will not be obtained

© Bose McKinney & Evans LLP

August 12, 2022

Preliminary, subject to change