## Slide 1: POLICE DEPARTMENT NEEDS ASSESSMENT PRESENTATION
TOWN OF MCCORDSVILLE

## Slide 2: AGENDA
VISIONING
NEEDS ASSESSMENT
ARCHITECTURAL SPACE PROGRAM
DIAGRAMMING
COST ESTIMATE
IMPLEMENTATION

## Slide 3: VISIONING
GOALS
The building is safe and secure for both staff and the public.
Attracts and retains staff– functionally and operationally efficient enabling staff to do their job well and improves their work experience.
Prominent, inviting visitors entrance– the building is being placed at a prominent corner of the town center development. A clear and visible entrance to the police station should be evident.
Supportive atmosphere for staff
Aesthetically pleasing building which embodies community pride by being an inviting and functional, while not being extravagant.
Ensures staff wellbeing by designing a building that is promotes healthy working environment. Staff productivity and mental well-being will increase because of this focus.
Quality materials that are low maintenance thereby making the early investment in better systems translates to more cost efficient in its utility usage and maintenance costs.

## Slide 4: NEEDS ASSESSMENT
On-site Interviews with the department leadership.
Data Collection across a every service area to enable extensive and objective analysis.
Iterative and Interactive Process in which the Consultant first understood the current organization and service delivery system, identified issues, and assessed current and future staffing needs. We conducted multiple meetings and interviews with key stakeholders.

## Slide 5: NEEDS ASSESSMENT

## Slide 6: ARCHITECTURAL SPACE PROGRAM

## Slide 7: DIAGRAMMING
SITE PLAN

## Slide 8: DIAGRAMMING
SITE PLAN

## Slide 9: COST ESTIMATE

## Slide 10: IMPLEMENTATION SCHEDULE
The implementation schedule is the recommendation of the Owner Representative and Consultant that advances this project to completion:
Approve the Resolution for the B.O.T. delivery model September 13, 2022
Solicit and select the B.O.T. delivery team 1 month
Develop GMP Documents 2 months
Approve the GMP and contract the B.O.T. team 1 month
Finalize the design 4 months
Permitting 1 month
Construction 14 months
Closeout & Occupancy 2 months (November 2024)