## Slide 1: Community Center Renovation Project
GMP & Project Budget
Town of McCordsville
Town Council
June 10, 2025

## Slide 2: Town Hall Project Overview
Activities To Date
Complete on Design
HVAC Evaluation & Engineering
Bidding
Ongoing FF&E Coordination
Key Scope Items
Primary Community Room
Auxiliary Meeting Space
Display Areas for VFD Memorabilia
Parks Dept. Offices
Next Steps
Establish GMP – June 10, 2025 council meeting
Value Engineering Review
Shop drawings & procurement ahead of construction start

## Slide 3: Community Center Budget & Bidding Updates
Estimated total project cost: $2.5 – 2.6M
  Guaranteed Maximum Price: $2,290,488 (bid amounts + CM fee + General Condition)
  Additional Project Costs: $230k - $330k
    Furniture
    AV/IT & Security
    Consultants
    Additional Site Construction
Focus Areas for Value Engineering
  Lighting, glazing, and finishes package
  Additional Project Costs: Scope of furniture and equipment package
  Detailed Plan Review for VE Opportunities with the architect, engineers, and construction manager
Overall Goal: Total Project Cost of $2.4 - $2.5M

## Slide 4: Additional Information
Schedule
Design Overview

## Slide 7: Design Highlights
Parking
Primary Building & Plaza

## Slide 8
Exterior Concept Rendering

## Slide 9: Design Highlights
Warming Kitchen
Large Community Room
Parks Dept Offices
Small Meeting Room

## Slide 10
Finishes