## Slide 1: Town of McCordsville
Wastewater Inventory Proposal

## Slide 2: Scope of work
Overview:
Waypoint Strategies will lead the development of an asset inventory and maintenance plan for the town’s wastewater treatment plant and associated lift stations. This project will include comprehensive data collection, evaluation, and planning efforts to ensure a structured and sustainable approach to asset management.
Key Scope Components:
Site Assessments & Data Collection
Asset Inventory
Condition & Useful Life Assessment
Preventative Maintenance Planning

## Slide 3: Schedule of Activities
Activity | Estimated Timeframe
Project Kick-off | April
Site Assessments & Data Collection | April - May
Asset Inventory Development | May – June
Condition Assessment & Useful Life Analysis | June – July
Preventative Maintenance Planning | June-July
Workbook Development & Reporting | July-August

## Slide 4: Asset and component inventory
The asset inventory will serve as a centralized repository of assets and associated components within the building. This list will streamline materials ordering for replacement and maintenance purposes, as well as asset information for more detailed or complex needs.

## Slide 5: Preventative maintenance & capital planning
This is a combination of worksheets that will work together to document routine preventative maintenance and build a 3-5 year capital investment plan for the building, providing near-term guidance for facilities management as well as long-term budget planning.