## Roadways
Capital Projects Plan
Roadway Projects
Project Number
Priority Level
Project Number
Year | SR 67 Median | Town Wide Crack Seal | Town-wide Patching | Misc. Design | Seal (franks, short to drives) | Cardinal Drive | MCR Widening (800N to 2nd) | 600W & 750N RAB | 700N Roundabout | 600W & 600N Intersection | Aurora Way RAB | McCord Rd Widening Need MOU w/ County | 750N Repair/resurface | 750N Streetscape (SR67 to 2nd TC RAB) | 900N & 600W RTL | 600 North Mill and Resurface (CCMG) need MOU w/ County | 600W & 500N Upgrades | 600N Blvd | Opticons (Broadway, 900, 600, 234, Carroll, Meijer) | 600W Corridor Prelim Eng Layouts | Hanna St & Center St - M & R | 700 West | Briarway Ln. | Terra Lane | Highland Lane | Crossfield Trail | Northview Court | Northview Drive | Ridgeway Court | Briarway Court | Coldwater Circle | Corel Reef | First Watch Way | Waterfront Way | Stormy Port | Schooner Circle | Bayside Circle | Oxford Ln | Emerald Blvd | Autumnview Drive | Commonview Drive | Glenview Drive | Springview Drive | Laredo Dr | Chelmsford Drive | Mallard Lane | Mallard Court | McCord Rd | 900N M & R - E of 600W | Aurora Way - P1 | Aurora Way - P2 | Annual Cost | Year
2022 |  | 37722.75 | 99180 | 40000 | 60000 |  | 500000 |  |  | 100000 |  |  |  |  | 140000 |  |  |  | 78000 | 25000 |  | 162600 | 96800 | 46200 | 53300 | 58500 | 13500 | 25900 | 17800 | 13800 | 9500 | 45800 | 40700 | 32600 | 15600 | 13900 | 8900 | 43900 | 70500 | 36200 | 54000 | 34500 | 18800 | 78300 | 59100 | 49600 | 7600 | 29000 | 103800 | 4726.19 | 850000 | 3175328.94 | 2022
2023 | 100000 | 40000 | 60000 | 40000 |  | 60000 | 1500000 |  | 50000 | 100000 |  | 80000 | 100000 |  |  | 150000 | 80000 |  |  |  | 70000 | [30 empty] | 2430000 | 2023
2024 |  | 40000 | 60000 | 40000 |  |  | 1500000 |  | 250000 | 63000 | 50000 | [40 empty] | 2003000 | 2024
2025 |  | 40000 | 60000 | 40000 |  |  | 1000000 | 50000 |  | 90000 | 250000 | 230000 | [39 empty] | 1760000 | 2025
2026 |  | 40000 | 60000 | 40000 |  |  | 375000 | 250000 | 500000 | [42 empty] | 1265000 | 2026
2027 |  | 40000 | 60000 | 40000 | [6 empty] | 500000 | [40 empty] | 640000 | 2027
2028 |  | 40000 | 60000 | 40000 |  |  |  | 500000 | [5 empty] | 300000 |  |  |  | 100000 | [33 empty] | 1040000 | 2028
Total Project Cost | 100000 | 277722.75 | 459180 | 280000 | 60000 | 60000 | 4875000 | 800000 | 800000 | 353000 | 800000 | 310000 | 100000 | 300000 | 140000 | 150000 | 80000 | 100000 | 78000 | 25000 | 70000 | 162600 | 96800 | 46200 | 53300 | 58500 | 13500 | 25900 | 17800 | 13800 | 9500 | 45800 | 40700 | 32600 | 15600 | 13900 | 8900 | 43900 | 70500 | 36200 | 54000 | 34500 | 18800 | 78300 | 59100 | 49600 | 7600 | 29000 | 103800 | 4726.19 | 850000 | 12313328.94 | Total Project Cost
FUND
General '22 | [51 empty] | 0 | General '22
General '23 | [51 empty] | 0 | General '23
General '24 | [51 empty] | 0 | General '24
General '25 | [51 empty] | 0 | General '25
General '26 | [51 empty] | 0 | General '26
General '27 | [51 empty] | 0 | General '27
General '28 | [51 empty] | 0 | MVH '21
MVH '22 |  |  |  | 40000 | 60000 |  |  |  |  | 100000 |  |  |  |  | 140000 |  |  |  | 78000 | 25000 |  | 40650 | 24200 | 11550 | 13325 | 14625 | 3375 | 6475 | 4450 | 3450 | 2375 | 11450 | 10175 | 8150 | 3900 | 3475 | 2225 | 10975 | 17625 | 9050 | 13500 | 8625 | 4700 | 19575 | 14775 | 12400 | 1900 | 7250 | 25950 | 25000 | 120000 | 898175 | MVH '22
MVH '23 |  | 40000 | 60000 | 40000 |  | 60000 |  |  | 50000 | 300000 |  | 80000 | 100000 |  |  | 150000 | 80000 |  |  |  | 70000 | [30 empty] | 1030000 | MVH '23
MVH '24 |  | 40000 | 60000 | 40000 |  |  |  |  | 250000 | 63000 | 50000 | [40 empty] | 503000 | MVH '24
MVH '25 |  | 40000 | 60000 | 40000 |  |  |  | 50000 |  | 90000 | 250000 | 230000 | [39 empty] | 760000 | MVH '25
MVH '26 |  | 40000 | 60000 | 40000 |  |  |  | 250000 | 500000 | [42 empty] | 890000 | MVH '26
MVH '27 |  | 40000 | 60000 | 40000 | [6 empty] | 500000 | [40 empty] | 640000 | MVH '27
MVH '28 |  | 40000 | 60000 | 40000 |  |  |  | 500000 | [5 empty] | 300000 |  |  |  | 100000 | [33 empty] | 1040000
LRS '22 | [51 empty] | 0 | LRS '22
LRS '23 | [51 empty] | 0 | LRS '23
LRS ' 24 | [51 empty] | 0 | LRS '24
LRS '25 | [51 empty] | 0 | LRS '25
LRS '26 | [51 empty] | 0 | LRS '26
LRS '27 | [51 empty] | 0 | LRS '27
LRS '28 | [51 empty] | 0
WWOP | [51 empty] | 0 | WWOP
CEDIT | [51 empty] | 0 | CEDIT
Rainy Day | 100000 | [5 empty] | 500000 | [43 empty] | 500000 | 1100000 | Rainy Day
Add'l Appropriation | [51 empty] | 0 | Add'l Appropriation
Aurora TIF | [51 empty] | 0 | Aurora TIF
Brookside TIF | [51 empty] | 0 | Brookside TIF
Broadway TIF | [51 empty] | 0 | Broadway TIF
Encumbered |  | 37722.75 | 99180 | [48 empty] | 136902.75 | Encumbered
Special LOIT | [51 empty] | 0 | Special LOIT
CCMG State Match | [21 empty] | 121950 | 72600 | 34650 | 39975 | 43875 | 10125 | 19425 | 13350 | 10350 | 7125 | 34350 | 30525 | 24450 | 11700 | 10425 | 6675 | 32925 | 52875 | 27150 | 40500 | 25875 | 14100 | 58725 | 44325 | 37200 | 5700 | 21750 | 77850 |  |  | 930525 | CCMG ST Match
Other | [6 empty] | 4375000 |  |  |  |  | 100000 | [38 empty] | 230000 | 4705000 | Other
*2023-2028 Projects are illustrative and listed for planning purposes.
Change Order Policy:
1. The PW Commissioner or Town Manager shall approve change orders of up to $5,000 in value.
2. The PW Committee Liaison from the Town Council shall approve change orders exceeding $5,000 in value.
3. Total change orders shall exceed 20% of the contract amount as required by IC 36-1-12-18.

## Multimodal
Capital Projects Plan
Multi-modal Projects | MVH & CEDIT Projects |  |  |  |  | PIF Projects |  |  |  |  | Grant Projects
Priority
Year | ADA Compliance | Trail Maintenance | 750N Ramps & Xwalks to Park | Broadway Sidewalk & Streetscape | Gap Acquisition | 800N - Mt. Comfort to Park (1/4 mile) | 750N - Kensington to Hampton Walk | Carroll Rd Trail - AT to WL | Mt. Comfort Sidewalk (750N to Town Center) | Parkland Acquisition | Old Town Alley Activation | 1000N Trail - 600W to MCP (3/4 mile) | Creekside Trail (1.75 miles) | Mt. Comfort - MES to 600N (1 mile) | Interuban/Depot | Yearly Cost
2022 | 20000 | 10000 | 20000 | 30000 | [11 empty] | 80000
2023 | 20000 | 10000 |  | 50000 |  |  |  |  | 450000 | [6 empty] | 530000
2024 | 20000 | 10000 | [6 empty] | 150000 | [6 empty] | 180000
2025 | 20000 | 10000 |  | 50000 |  |  | 15000 | 30000 | [7 empty] | 125000
2026 | 20000 | 10000 |  | 50000 |  |  | 100000 | 100000 | [7 empty] | 280000
2027 | 20000 | 10000 |  | 50000 | [11 empty] | 80000
2028 | 20000 | 10000 |  | 50000 | [11 empty] | 80000
Total Project Cost | 140000 | 70000 | 20000 | 280000 | 0 | 0 | 115000 | 130000 | 600000 |  | 0 | 0 | 0 | 0 | 0 | 1355000
FUND
MVH '22 | 20000 | 10000 | 20000 | [12 empty] | 50000
MVH '23 | 20000 | 10000 |  | 20000 | [11 empty] | 50000
MVH '24 | 20000 | 10000 | [6 empty] | 20000 | [6 empty] | 50000
MVH '25 | 20000 | 10000 |  | 20000 | [11 empty] | 50000
MVH '26 | 20000 | 10000 |  | 20000 | [11 empty] | 50000
MVH '27 | 20000 | 10000 |  | 20000 | [11 empty] | 50000
MVH '28 | 20000 | 10000 |  | 20000 | [11 empty] | 50000
CEDIT '22 |  |  |  | 30000 | [11 empty] | 30000
CEDIT '23 |  |  |  | 30000 | [11 empty] | 30000
CEDIT '24 | [8 empty] | 30000 | [6 empty] | 30000
CEDIT '25 |  |  |  | 30000 | [11 empty] | 30000
CEDIT '26 |  |  |  | 30000 | [11 empty] | 30000
CEDIT '27 |  |  |  | 30000 | [11 empty] | 30000
CEDIT '28 |  |  |  | 30000 | [11 empty] | 30000
Rainy Day | [15 empty] | 0
Add'l Appropriation | [15 empty] | 0
Brookside TIF | [15 empty] | 0
Broadway TIF | [15 empty] | 0
Encumbered | [15 empty] | 0
Special LOIT | [15 empty] | 0
Grant Match | [15 empty] | 0
PIF | [6 empty] | 130000 |  | 450000 | [6 empty] | 580000
Other | [8 empty] | 100000 | [6 empty] | 100000
Notes | [7 empty] | Acquisition & Design on trail gaps. |  |  | Activation of E-W alley (south of MUMC) to a shared use street. | May be beneficial to acquire land in advance. | May be beneficial to acquire land in advance. | Scope changes if Hampton Walk & Lain Farms are approved.
*2023-2028 Projects are illustrative and listed for planning purposes.

## WW STR
Capital Projects Plan
Wastewater and Stormwater
Project Number
Year | Stansbury Force Main & Lift Station | WW Treatment Plant Construction | WWTP Equipment | Manhole Rehabilitation | CR 800 N Ditch | Center & Hanna & Broadway | N. Railroad St. | Town Center Stormwater Park | 800N Drainage |  | Annual Costs
2022 | 200000 | 460000 | 10000 | 25000 | 340250 | 317745 |  |  | 100000 |  | 1452995
2023 |  |  |  | 25000 |  |  |  | XXXX | 250000 |  | 275000
2024 |  |  |  | 25000 |  |  | 300000 |  |  |  | 325000
2025 |  |  |  | 25000 | [6 empty] | 25000
2026 |  |  |  | 25000 | [6 empty] | 25000
2027 |  |  |  | 25000 | [6 empty] | 25000
2028 |  |  |  | 25000 | [6 empty] | 25000
Total Project Cost | 200000 | 460000 | 10000 | 175000 | 340250 | 317745 | 300000 | 0 | 350000 | 0 | 2152995
FUND
CCI '22 | [10 empty] | 0
CCI '23 | [10 empty] | 0
CCI '24 | [10 empty] | 0
CCI '25 | [10 empty] | 0
CCI '26 | [10 empty] | 0
CCI '27 | [10 empty] | 0
CCI '28 | [10 empty] | 0
WW OP '22 |  |  |  | 25000 | [6 empty] | 25000
WW OP '23 |  |  |  | 25000 | [6 empty] | 25000
WW OP '24 |  |  |  | 25000 | [6 empty] | 25000
WW OP '25 |  |  |  | 25000 | [6 empty] | 25000
WW OP '26 |  |  |  | 25000 | [6 empty] | 25000
WW OP '27 |  |  |  | 25000 | [6 empty] | 25000
WW OP '28 |  |  |  | 25000 | [6 empty] | 25000
ST WTR '22 |  |  |  |  | 340250 | 317745 |  |  | 100000 |  | 757995
ST WTR '23 | [10 empty] | 0
ST WTR '24 | [6 empty] | 300000 |  |  |  | 300000
ST WTR '25 | [10 empty] | 0
ST WTR '26 | [10 empty] | 0
ST WTR '27 | [10 empty] | 0
ST WTR '28 | [10 empty] | 0
SIB '22 | 200000 | [9 empty] | 200000
SIB '23 | [10 empty] | 0
SIB '24 | [10 empty] | 0
SIB '25 | [10 empty] | 0
SIB '26 | [10 empty] | 0
SIB '27 | [10 empty] | 0
SIB '28
Rainy Day | [10 empty] | 0
Add'l Appropriation | [10 empty] | 0
Brookside TIF | [10 empty] | 0
Broadway TIF | [10 empty] | 0
Bond | [10 empty] | 0
Encumbered | [10 empty] | 0
Other | [10 empty] | 0
*2023-2028 Projects are illustrative and listed for planning purposes.

## O&M
Capital Projects Plan
Operations, Maintenance, Parks, & Studies
| Operations/Vehicles/Maintenance | [19 empty] | Studies/Plans |  |  |  | Parks
Project Number
Year | 34K GVW Truck | PW 650 Truck #23 | Street sweeeper #19 | PW 450 Truck #09 |  | Eng Vehicle #19 | PW 2500 Truck #10 | Rollback Truck | Rolloffs (4) | PW 2500 Truck #11 | Planning Vehicle #14 | Planning Vehicle #XX | Planning Vehicle #16 | Generator (Replacement) | Park 2500 Truck (New) | Road Maintenance Equipment (New) | Public Works Equipment (New) | Tractor Replacement | GIS Mapping | IT Upgrades | Comp Plan Update | Plan Updates/Studies/Design | RIF Study | Sanitary Sewer Master Plan Update | Town Center Infrastructure Bond | Old School Park Improvements | Crushed Stonewalk | Yearly Costs
2022 |  | 5612 | 25403 |  |  | 4719.2 | 6000 |  |  |  |  | 12000 |  |  |  |  | 80000 | ? | 12000 | 8000 | 37500 | 20000 | 100000 | 20000 | 4300000 | 6000 | 20000 | 4657234.2
2023 | 40000 | 5612 | 25403 | 17000 |  | 4719.2 | 6000 | 220000 | 60000 | 6000 |  |  |  |  | 6000 | [6 empty] | 20000 |  | 20000 |  |  |  | 430734.2
2024 | 40000 | 5612 |  | 17000 |  | 4719.2 | 6000 |  |  | 6000 |  |  |  | 90000 | 6000 | 40000 | [5 empty] | 20000 | [5 empty] | 235331.2
2025 | 40000 |  |  | 17000 |  |  | 6000 |  |  | 6000 |  |  |  |  | 6000 | [6 empty] | 20000 | [5 empty] | 95000
2026 | 40000 |  |  | 17000 |  |  | 6000 |  |  | 6000 | 6000 |  |  |  | 6000 | [6 empty] | 20000 | [5 empty] | 101000
2027 | 40000 |  |  | 17000 | [5 empty] | 6000 | 6000 |  |  |  | 6000 | [6 empty] | 20000 | [5 empty] | 95000
2028 | [10 empty] | 6000 | [10 empty] | 20000 | [5 empty] | 26000
Total Project Cost | 200000 | 16836 | 50806 | 85000 | 0 | 14157.6 | 30000 | 220000 | 60000 | 30000 | 18000 | 12000 | 0 | 90000 | 30000 | 40000 | 80000 |  | 12000 | 8000 | 37500 | 140000 | 100000 | 40000 | 4300000 | 6000 | 20000 | 5640299.6
FUND
General '22 | [19 empty] | 8000 |  | 20000 |  |  |  | 6000 |  | 34000
General '23 | [14 empty] | 6000 | [6 empty] | 20000 | [5 empty] | 26000
General '24 | [14 empty] | 6000 | [6 empty] | 20000 | [5 empty] | 26000
General '25 | [14 empty] | 6000 | [6 empty] | 20000 | [5 empty] | 26000
General '26 | [10 empty] | 6000 |  |  |  | 6000 | [6 empty] | 20000 | [5 empty] | 32000
General '27 | [10 empty] | 6000 |  |  |  | 60000 | [6 empty] | 20000 | [5 empty] | 86000
General '28 | [10 empty] | 6000 | [10 empty] | 20000 | [5 empty] | 26000
MVH '22 | [5 empty] | 1573 | [10 empty] | 20000 | [10 empty] | 21573
MVH '23 |  |  |  | 17000 |  | 1573 | [21 empty] | 18573
MVH '24 |  |  |  | 17000 |  | 1573 | [21 empty] | 18573
MVH '25 |  |  |  | 17000 | [23 empty] | 17000
MVH '26 |  |  |  | 17000 | [23 empty] | 17000
MVH '27 |  |  |  | 17000 | [23 empty] | 17000
MVH '28 | [27 empty] | 0
LRS '22 |  | 5612 | 25403 | [24 empty] | 31015
LRS '23 | 40000 | 5612 | 25403 | [24 empty] | 71015
LRS '24 | 40000 | 5612 | [13 empty] | 40000 | [11 empty] | 85612
LRS '25 | 40000 | [26 empty] | 40000
LRS '26 | 40000 | [26 empty] | 40000
LRS '27 | 40000 | [26 empty] | 40000
LRS '28 | [27 empty] | 0
CEDIT '22 | [27 empty] | 0
CEDIT '23 | [27 empty] | 0
CEDIT '24 | [27 empty] | 0
CEDIT '25 | [27 empty] | 0
CEDIT '26 | [27 empty] | 0
CEDIT '27 | [27 empty] | 0
CEDIT '28 | [27 empty] | 0
WW OP '22 | [5 empty] | 1573 | 6000 | [9 empty] | 20000 | [6 empty] | 20000 |  |  |  | 47573
WW OP '23 | [5 empty] | 1573 | 6000 |  |  | 6000 | [13 empty] | 20000 |  |  |  | 33573
WW OP '24 | [5 empty] | 1573 | 6000 |  |  | 6000 |  |  |  | 90000 | [13 empty] | 103573
WW OP '25 | [6 empty] | 6000 |  |  | 6000 | [17 empty] | 12000
WW OP '26 | [6 empty] | 6000 |  |  | 6000 | [17 empty] | 12000
WW OP '27 | [9 empty] | 6000 | [17 empty] | 6000
WW OP '28 |  |  | 15403 | [24 empty] | 15403
ST WTR '22 |  |  | 15403 |  |  | 1573 | [10 empty] | 20000 | [10 empty] | 36976
ST WTR '23 |  |  | 15403 |  |  | 1573 | [21 empty] | 16976
ST WTR '24 | [5 empty] | 1573 | [21 empty] | 1573
ST WTR '25 | [27 empty] | 0
ST WTR '26 | [27 empty] | 0
ST WTR '27 | [27 empty] | 0
ST WTR '28 | [27 empty] | 0
Rainy Day | [11 empty] | 12000 | [15 empty] | 12000
Add'l Appropriation | [27 empty] | 0
Brookside TIF | [27 empty] | 0
Broadway TIF | [24 empty] | 4300000 |  |  | 4300000
Encumbrance | [18 empty] | 12000 |  |  | 37500 | [5 empty] | 49500
SIB | [7 empty] | 220000 | 60000 | [18 empty] | 280000
CCI | [14 empty] | 30000 | [12 empty] | 30000
Other | [27 empty] | 0
Notes
*2023-2028 Projects are illustrative and listed for planning purposes.
A=Rainy Day funds initial purchase, to be re-paid from applicable fund over years listed.
B=Repayments to Rainy Day Fund